## Slide 1: Onboarding Slides
Supplied by Adam Hannemann
https://adamhannemann.com
https://linkedin.com/in/ahannemann

## Slide 2
Pieces of the Onboarding Puzzle
New client onboarding requires several pieces to complete the puzzle.
Tool Installation
Client Experience
Old MSP Tools removed and ours installed
Tech checks-in
Computers may be rebooted
MSP Tasks
Old tools removed/new tools installed
User check-ins / pain point interviews
Issue Cleanup
Client Experience
Issues start getting resolved
MSP Tasks
Log tickets for issues
Work issues as appropriate
Go-Live
Client Experience
Attends “Go-Live” meeting
Starts reaching out for support
MSP Tasks
Holds ”Go-Live” meeting
Trains client on how to obtain support
Info Gathering & Documentation
Client Experience
Provide info to onboarding team
Attend Kick-Off meeting
MSP Tasks
Attend Kick-Off Meeting
Document network infrastructure, LOBs, and core processes

## Slide 3
Client Onboarding Day-by-Day
Day 1: Documentation
MSP Tasks:
Document core network / server infrastructure
Document LOB apps
Install RMM tools on Servers
Update Client
Day 2: Tool Deployment
Day 3: Continuing Tools & Docs
Day 4: Work User Issues
Day 5: Go-Live
Client Experience:
Key members of client may be consulted for system / LOB info
Client main contact provides further info as necessary
MSP Tasks:
Install RMM agent, Security Stack, and other tools
Label computers
Gather user issues
Update Client
Client Experience:
Old tools removed and new tools installed
Computer may be rebooted
Tech stops by and gathers info
MSP Tasks:
Continue Documenting network as needed
Finish installing tools
Create tickets for user issues
Update Client
Client Experience:
Same as Day 2
MSP Tasks:
Work to solve as many user issues as possible
Wrap up any open documentation tasks
Update Client
Client Experience:
Issues start getting solved
MSP Tasks:
Go-Live training held
Teach users how to get support
Helpdesk notified that client is now “live”
Update Client
Client Experience:
Attend Go-Live training
Start calling Helpdesk for support
Day-by-day breakdown of what a client should expect throughout the process

## Slide 4
Onboarding Checklist
This is a high-level checklist of what info we need, data we document, and how we hand-off support to the Helpdesk
Info Gathering
Documentation
Hand-off to Support
Info FROM Client
Admin passwords
Previous MSP documentation & Contact Info
Internet provider(s)
Voice provider(s)
Web host & Domain Registrar
Email info
LOB App Information
Printer/Copier Info
Physical security
Cyber Insurance Info
Collaboration tools (SharePoint, Teams, Slack, etc.)
Cloud Storage (Dropbox, Box, OneDrive, etc.)
Technical Documentation
Firewall(s)
Server(s)
Network & WiFi
Line of business apps
Printers
Email, domain name(s), & web hosts
File share/storage
Backups
Remote access
A/V QC + Security documentation
Process Documentation
New user setup
New computer setup
Hand-Off Process
New partner “Go-Live” meeting
How to obtain support training and document
Roadmap created
Helpdesk hand-off meeting with Onboarding Engineer
NOTE: Admin passwords are required to start the onboarding.

## Slide 5
Onboarding Responsibilities
These are the high-level tasks assigned to each of the main roles in the onboarding process.
Project Manager
Manage project from start-finish
Schedule and attend meetings
Manage tech schedules
Make sure that ongoing communication is happening
Account Management
Attend/facilitate meetings
Run the Go-Live meeting with client
Provide how to obtain support training to client
Work with client contacts to schedule first SBR
Onboarding Technician
Document client environment
Deploy tools / Security Stack
Label Equipment & Computers
Capture user related issues and solve where appropriate
Hand-off support to Service Team
Client
Provide information to MSP for systems, passwords, and any documentation
Attend meetings
Facilitate staff availability
Reenforce importance of participating in onboarding