## High Level Project Plan
WBS # | Category Name | Deliverable | Status
1.1 | Planning
1.1.1 | Project Plan | Create project plan for the full Acquisition including full WBS, Project Plan, and related documents.
1.1.2 | Maturity & Size Comparison | Compare the two organizations to understand where each side of the transaction has more maturity. Also, consider size comparisons in this conversation.
1.2 | Human Resources
1.2.1 | Benefits | Determine how and what the updated benefit package will be for acquired employees and steps to enroll in an efficient manner.
1.2.2 | Payroll | Complete consolidation of payroll activities, ensure that employees get paid on-time, and communicate updates to all employees.
1.2.3 | Accountability/Org Chart | Create updated accountability/organization chart for merged company complete with names assigned.
1.2.4 | Onboarding | Complete onboarding of acquired employees. Complete all paperwork, get benefits assigned, and be ready to complete first payroll.
1.2.5 | Team Communication | Build a communication plan for employees to bring everyone to the same page. Including introductions, what the acquired employees can expect, and next steps.
1.3 | Legal/Insurance
1.3.1 | Managing the Deal | Work with all relevant parties to get the deal closed and paperwork signed.
1.3.2 | Insurance | Work with insurance broker/carriers to ensure that the acquisition assets are covered with policies and adjust as needed.
1.3.3 | Leases | If acquiring a company that leases space ensure that the lease is reviewed and landlord is updated with the status of the company.
1.3.4 | Banking | Work with relevant banks to ensure there is enough operating capital for post acquisition activities. Also ensure that bank accounts and cash will be available as required. Finally consider opening a line of credit on the acquisition side just in case a cash infusion is needed.
1.3.5 | Taxes | Work with CPA firm and/or a tax attorney to make sure all records are in order to file taxes. If in a different state, work to understand, the sales tax laws in the additional state.
1.4 | Finance
1.4.1 | Chart of Accounts | Review financial books of acquired company to align the various chart of accounts related activities. Adjust chart of accounts as required.
1.4.2 | Budget/Forecast | Review the profit and loss statement of the acquired company and integrate their revenue, cost of good sold, and expenses into your budget
1.4.3 | AR/Invoicing | Update the invoicing process to accept invoices from the acquired companies PSA until all contracts/agreements, projects, and time and material billing is moved to the acquiring companies set of books.
1.4.4 | AP/Vendors | Contact existing vendors and notify them of the acquisition. Migrate/create lines of credit and other related vendor paperwork for the acquisition.
1.4.5 | Expense Management | Document and train the new employees on the expense process. Ensure all that require company cards receive them, and all personnel understand how to submit expenses for reimbursement.
1.5 | Sales/Marketing
1.5.1 | Branding | Update, branding and marketing assets if appropriate.
1.5.2 | External Marketing | Create marketing plan to announce the acquisition, the benefits, and how excited everybody is for the now larger organization, and the benefits for all included.
1.5.3 | Sales Team | Review, update, and reach out to any active leads in the sales pipeline. Let them know how this acquisition benefits them, and why now is the time to sign with you.
1.5.4 | Account Management | If acquired company has account management practice, work to integrate that practice into the acquiring companies, account management, practice, and process. Reach out to all impacted clients to check in, set next meeting, and answer any questions that they may have. Large clients may require a site visit.
1.6 | Operations
1.6.1 | Stack | Review acquired company, stack, and make plan to consolidate into your stack. If appropriate, if acquired company has better stack items, consider migrating in the other direction for those items. Build complete plan for migration, and prepare for execution of said plan.
1.6.2 | Service | If adding members to the service team, train new service, team members on process, and work to build one cohesive team.
1.6.3 | Projects | If adding members to the project team, train new project, team members, and work to build cohesive project team. Also review all projects currently in progress, and make plan to complete project inside, former PSA, or migrate to new PSA.
1.6.4 | NOC / SOC | If adding members to your NOC/SOC team, train them on new processes, and learn how existing clients are monitored and managed. Make a plan for transition, and ensure your team is on board.
1.6.7 | Field / Augmentation / Co-Managed | For all field related engineers/situations, and ensure that the new team is up-to-date, and able to support their clients. Create/update any plans for cross team, collaboration, and cross training.
1.6.8 | Automation | Review any active automations on the acquired side to understand how they may be leveraged in the acquiring side. Where possible, upgrade automations between the two organizations.
1.7 | Tool Consolidation
1.7.1 | Planning | Review the tool set of the acquired company, and build a master plan for how to integrate the tool sets together, and how to on board all acquired clients into the updated system. Also consider updating existing clients if any tool changes are made in the other direction.
1.7.2 | O365 Consolidation | Consolidate two O365 tenants into one. Ensure that delegated access to client accounts is not lost.
1.7.3 | PSA | Create detailed plan to move client data from acquired side PSA into acquiring PSA. Ensure that all clients, client contacts, contracts, and any important operational data is included. Consider not moving existing ticket data.
1.7.4 | Accounting Systems | Create detailed plan to integrate the acquired companies books into your accounting package.
1.7.5 | Payment Portal | Create plan to migrate clients from acquired sides portal to acquiring portal. Account for client training, account, manager, training, and service desk training.
1.7.6 | RMM / Remote Control | Create plan to migrate end points from acquired side's, RMM/Remote Control into acquiring sides RMM. Where possible, automate as much of this as you can.
1.7.7 | Phone System | Determine process and plan for moving key phone numbers from acquired company's phone system.
1.7.8 | Documentation | Create plan to migrate important documentation to acquiring companies system. Ensure that no key data is lost, and there is a transition plan to get to a single documentation system as quickly as possible.
1.7.9 | Other Tools | Make plans to migrate all other core tools to acquiring company's systems and standards.
1.7.10 | Network Infrastructure | Create plan to integrate any core network infrastructure to acquired company's network.
1.7.11 | Account Management Tools / Quoting | Plan for the migration of all account management related tools to a single account management system. Include xBR/SBR related tools, quoting tools, and any additional client facing tools as required.