## Checklist
Info Needed from Client |  | Technical Documentation |  | Core Onboarding Tasks
FALSE | Admin Passwords |  | Network Information |  | Toolset
FALSE | Previous MSP Info | FALSE | ISP Information | FALSE | RMM Deployment
FALSE | Internet Provider Info | FALSE | Firewall(s) | FALSE | Old Tool Removal
FALSE | Voice Provider Info | FALSE | Switch(es) | FALSE | Security Tools Deployment
FALSE | Web Hosting Info | FALSE | WiFi |  | Documentation & Training
FALSE | Domain Name/DNS Info |  | Server Information | FALSE | Documentation Complete
FALSE | Email Provider Info | FALSE | On Prem Servers | FALSE | Roadmap Complete
FALSE | LOB App Contact Info | FALSE | Cloud Servers | FALSE | Hand-Off to Service Desk
FALSE | Printer Support Info | FALSE | Printer Information | FALSE | Capture open issues with users
FALSE | Physical Security Info | FALSE | File Shares / Storage Location |  | Client Go-Live Activiites
FALSE | Cyber Insurance Info |  | Backup Information | FALSE | Portal access given to client
FALSE | Employee info (list of employees) | FALSE | Cloud Backup | FALSE | Onboarding Meeting / How to obtain support
FALSE | Who has authority to spend money? | FALSE | Server Backup | FALSE | Schedule first xBR
FALSE | Who approves new users? | FALSE | Workstation Backup
FALSE | Who approves different permissions? |  | Security Information
|  | FALSE | AV/EDR/MDR/xDR
|  | FALSE | Email Security (SPAM, DKIM, DMARC)
|  | FALSE | DNS Filtering / Web Security
Web/Email Information
|  | FALSE | Email Information (Mail Host, MX, etc.)
|  | FALSE | Web hosting information
|  | FALSE | DNS information
Process Info
|  | FALSE | New User Setup
|  | FALSE | New Computer Setup
|  | FALSE | LOB Specific Documentation
|  | FALSE | Remote Access Setup
|  | FALSE | What = Client Online

## Project Plan
| Task | Notes
1 | Pre-Onboarding
1.1 | Agreements Signed
1.2 | Sales hand-off to Project Team
1.3 | Kick-Off Meeting with new client
1.4 | Client sends over documentation
1.5 | Create Documentation "shells" in system
2 | Onboarding
2.1 | Tool Deployment
2.1.1 | Remove old agents & security tools
2.1.2 | Install new RMM agents
2.1.3 | Deploy new security tools
2.2 | Documentation
2.2.1 | Document Network Information
2.2.2 | Document Server Information
2.2.3 | Document Backup Information
2.2.4 | Document Security Information
2.2.5 | Document Web/Email Information
2.2.6 | Document Process Information
2.2.7 | Document what it means for client to be UP
2.3 | Roadmap Creation
2.3.1 | Work with Account Management / Sales to build roadmap
2.4 | User Issues
2.4.1 | Capture user issues into ticketing system
2.4.2 | Solve as many as possible
2.4.3 | Hand-off remainder to Service Desk
3 | Hand-Off
3.1 | Train Service Desk on new client
3.2 | Schedule Hand-Off meeting with client
3.3 | Train client on how to get support / provide document
3.4 | Attend hand-off meeting and answer questions
3.5 | Client is now live